## Sheet1
Communication Plan
Communication | Method | Frequency/Schedules | Goal | Responsible Person | Audience
Project status report | Email | Weekly | Review the status of the project and talk about any problems or delays. | Project manager | Project team + Project sponsor
Team standup | Meeting | Daily | Talk about the actions taken by each team member yesterday, what they'll do today, and any challenges. | Project manager | Development team
Project review | Meeting | At milestones | Present the project outputs, get feedback, and talk about the future stages. | Project manager | Project team + Project sponsor
Post-mortem meeting | Meeting | At end of the project | Examine what worked and what did not work, and consider takeaways that might be used. | Project manager | Project team
Task progress updates | TeamGantt | Daily | Share your daily progress on project assignments. | Project manager | Project team
|  |  |  | Created By, | Jigar Patel
Smit Arora
Dhrumi Patel