## WBS
Work Breakdown Structure
No | Type of task | Description of task | Outputs deliverables | Responsible person(s) | Dead- line
| Project time |  |  |  | 15th Septemer - 15th December
1 | Hiring Process
1.1 | Hire an IT team | Create a team with a leader who are excellence in making website | Plan, gather and one goal mindset | Jigar Patel | 25th September
1.2 | Hire a HR team | Create a HR team for one to one conversation for interview process | Plan, gather and one goal mindset | Jigar Patel | 25th September
1.3 | Hire different experts form their fields | To create materials | Plan, gather and one goal mindset | Jigar Patel | 25th September
2 | Webpage Development/Design
2.1 | Making structure of the frontend | Template designing | Paper design ready | Bhakti Bhatt (IT Lead) | 29th September
2.2 | Implementing the structure into webpage | Completing frontend with React JS | Phase 1 with 50% of buttons added | Bhakti Bhatt (IT Lead) | 14th October
2.3 | Working on backend | Start working on backend with .Net language. | Phase 2 with our website | Bhakti Bhatt (IT Lead) | 28th October
2.4 | Create a Database | Make connection with our website | Phase 3 establishing connection between database and website | Bhakti Bhatt (IT Lead) | 15th October
2.5 | Checking on all features | Putting all buttons and features required | Layout ready | Bhakti Bhatt (IT Lead) | 2nd October
2.6 | Final Testing | Testing and QA team start working on testing | Website was tested on every aspect | Bhakti Bhatt (IT Lead) | 10th October
3 | Managing HR staff and Experts
3.1 | Experts make their own articles and videos | Putting the data into Data frame as per model requirements | Materials for interview | Dhrumi Patel (Co-ordinator) | 10th November
3.2 | HR making their schedules | They are making their own availibility for our website only | Schedule for 1 on 1 interview | Dhrumi Patel (Co-ordinator) | 15th November
3.3 | Cheking all the materials | Check and verify all the materials before uploading it | For giving quality content we took each needed step | Dhrumi Patel (Co-ordinator) | 1st December
4 | Closing Report
4.1 | Handover Website | Handover website to client | Fully functional website | Jigar Patel ¦ Smit Arora ¦ Vismay Lad | 15th Decemer
|  |  |  | Created by , | Jigar Patel
Dhrumi Patel
Bhakti Bhatt
Smit Arora
Vismay Lad