## Project Budget
| Project Name: | Interview preparation website
| Project Manager Name: | Jigar Patel
|  |  |  | Labor |  | Materials | [6 empty] | BALANCE
|  |  | Planned Hours | Actual Hours | $/HR | UNITS | $/UNITS | Travel | Equipment | Misc. | BUDGETED | ACTUAL | UNDER/OVER
WBS | Project Tasks | Assigned To: | [8 empty] | 145000 | 139020 | 5980
1 | Hiring Process
1.1 | Hire an IT team | Jigar Patel | 300 | 250 | 38 |  |  | 3000 | 6500 | 200 | 21100 | 19200 | 1900
1.3 | Hire a HR team | Jigar Patel | 170 | 160 | 35 | [5 empty] | 5950 | 5600 | 350
1.4 | Hire different experts form their fields | Jigar Patel | 100 | 60 | 35 | [5 empty] | 3500 | 2100 | 1400
[11 empty] | 0 | 0 | 0
2 | Webpage Development/Design | [9 empty] | 0 | 0 | 0
2.1 | Making structure of the frontend | Bhakti Bhatt (IT Lead) | 100 | 70 | 28 |  |  | 0 | 10000 | 500 | 13300 | 12460 | 840
2.2 | Implementing the structure into webpage | Bhakti Bhatt (IT Lead) | 450 | 400 | 28 | [5 empty] | 12600 | 11200 | 1400
2.3 | Working on backend | Bhakti Bhatt (IT Lead) | 350 | 375 | 28 | [5 empty] | 9800 | 10500 | -700
2.4 | Create a Database | Bhakti Bhatt (IT Lead) | 300 | 230 | 28 | [5 empty] | 8400 | 6440 | 1960
2.5 | Checking on all features | Bhakti Bhatt (IT Lead) | 70 | 65 | 32 | [5 empty] | 2240 | 2080 | 160
2.6 | Final Testing | Bhakti Bhatt (IT Lead) | 210 | 200 | 25 | [5 empty] | 5250 | 5000 | 250
[11 empty] | 0 | 0 | 0
3 | Managing HR staff and Experts | [9 empty] | 0 | 0 | 0
3.1 | Experts make their own articles and videos | Dhrumi Patel (Co-ordinator) | 910 | 945 | 34 |  |  | 0 | 7050 | 0 | 37990 | 39180 | -1190
3.2 | HR making their schedules | Dhrumi Patel (Co-ordinator) | 80 | 58 | 30 | [5 empty] | 2400 | 1740 | 660
3.3 | Checking all the materials | Dhrumi Patel (Co-ordinator) | 1070 | 1120 | 21 | [5 empty] | 22470 | 23520 | -1050
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
[11 empty] | 0 | 0 | 0
| SUBTOTAL |  |  |  | 111770 |  | 0 | 3000 | 23550 | 700 | 145000 | 139020 | 5980
Created by:- Smit Arora
Vismay Lad