## GANTT CHART
Interview Preparation Website
Created on - |  | 15th April
Created By - |  | Jigar Patel, Vismay Lad, Bhakti Bhatt
Task | Start Date | End Date | Duration (In Days)
Hire an IT team | 2022-09-15 | 2022-09-25 | 10
Hire a HR team | 2022-09-16 | 2022-09-25 | 9
Hire different experts form their fields | 2022-09-16 | 2022-09-25 | 9
Making structure of the frontend | 2022-09-19 | 2022-09-29 | 10
Experts make their own articles and videos | 2022-09-30 | 2022-11-10 | 41
Implementing the structure into webpage | 2022-10-01 | 2022-10-14 | 13
Working on backend | 2022-10-14 | 2022-10-28 | 14
Create a Database | 2022-11-01 | 2022-11-15 | 14
HR making their schedules | 2022-11-10 | 2022-11-15 | 5
Cheking all the materials | 2022-11-15 | 2022-12-01 | 16
Checking on all features | 2022-11-20 | 2022-12-02 | 12
Final Testing | 2022-12-01 | 2022-12-10 | 9
Website handover | 2022-12-10 | 2022-12-15 | 5
44819
|  |  |  | Created by, | Jigar Patel
Bhakti Patel